## Jira
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date
Bug | DAS-3 | 10180 | Spelling mistake in warning message displayed on invalid data upload in Dashboard module | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Medium | To Do |  | 2026-04-16 11:21 | 2026-04-16 11:21
Bug | DAS-4 | 10181 | Unnecessary message displayed after downloading a sheet | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Low | To Do |  | 2026-04-16 11:25 | 2026-04-18 09:48
Bug | DAS-5 | 10182 | Downloaded overtime sheet is not properly formatted and data is misaligned in Excel file | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | High | To Do |  | 2026-04-16 11:30 | 2026-04-16 11:31
Bug | DAS-6 | 10183 | System allows Excel file upload even when required options are not selected | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | High | To Do |  | 2026-04-16 11:37 | 2026-04-16 11:37
Bug | DAS-7 | 10184 | Incorrect validation message displayed for missing HRMS and Attendance files | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | High | To Do |  | 2026-04-16 11:41 | 2026-04-16 11:41
Bug | DAS-8 | 10185 | Spelling mistake in placeholder text (“No file chosen”) across multiple file upload fields in Dashboard module | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Medium | To Do |  | 2026-04-16 11:47 | 2026-04-16 11:47
Bug | DAS-9 | 10186 | Search, Edit, Delete, and Add buttons are not functioning in User Mapping module | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Highest | To Do |  | 2026-04-16 11:51 | 2026-04-16 11:53
Bug | DAS-10 | 10219 | Name field in State module accepts numeric values and special characters | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Medium | To Do |  | 2026-04-20 11:45 | 2026-04-20 11:45
Bug | DAS-11 | 10220 | Search functionality fails for city names with more than three characters in Location module | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Medium | To Do |  | 2026-04-20 11:49 | 2026-04-20 11:49
Bug | DAS-12 | 10221 | Database warning messages displayed during search operation in Add Entity module | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | Aditya Jadhav | 712020:a6c9ba74-cb69-459e-9955-b20111a335d3 | High | To Do |  | 2026-04-20 11:52 | 2026-04-20 11:53